## 1 GIA
Gender impact assessments
Table 1 - Gender impact assessments progress
Required | Required | Required | Required | Required | Required | Recommended | Recommended
Title | Subject | Description | Status | Confirm if actions taken | Describe actions taken | Confirm intersectionality considered | Explain intersectional lens applied
What is the title of the policy, program or service that was the subject of the GIA? Please use one row for each GIA completed. When reporting on multiple actions taken, include this information in the relevant single cell. | Was the subject of the GIA a policy, program or service? For definitions of policies, programs and services, please refer to the guidance materials at Appendix A: Glossary of terms. Use the drop-down menu in the cell to select your answer. | Provide a description of the policy, program or service subject to the GIA. | Was the policy, program or service new, or up for review? Use the drop-down menu in the cell to select your answer. | Were actions taken to develop or vary the policy, program or service to meet the needs of people of different genders, address gender inequality and promote gender equality as a result of the GIA? Use the drop-down menu in the cell to indicate whether or not actions were taken as a result of the GIA. | Describe the actions taken to develop or vary the policy, program or service to meet the needs of people of different genders, address gender inequality and promote gender equality. When reporting on multiple actions taken, include this information in one cell. You can press alt+enter to include new lines. | Was it considered that gender inequality may be compounded by disadvantage or discrimination that people may experience on the basis of intersectionality? Use the drop-down menu in the cell to select your answer. | Explain how an intersectional lens was applied while completing the GIA. If this was not done, explain why this was not practicable.
Title | Subject | Description | Status | Confirm if actions taken | Describe actions taken | Confirm intersectionality considered | Explain intersectional lens applied
ED AI trial tool development | program | Develop of a framework for AI to help predict flow through the Emergency Dept | New | yes | data collection plan amended to capture gender and other identty markers to support decsion making and asess any differences
Review of workflows to improve idenitification of patients to better link in with relevent services and to improve data capture | service | Review process within existing services to identify when extra supports may be useful | review | yes | "Refugees Homeless Disability ""Whatt matters"" future projects identified - will be included in consumer/carer engagement strategy" | Yes | considered the multiple aspects of a patient that may intersect to increase possible vulnerale and supports needed
review email sent in response to sexual harassment riskman | policy | Email sent to staff after reporting sexual harassment informing them of process etc. | review | yes | much more personalised and senstive email
bathrooms in basement | service | design and develop a new change/bathroom facility at city campus | new | yes | increase number of all gender bathroms, lockers provided outside of gendered shower/change spaces for inclusive access | Yes | Also increased total number of accessible shower/change spaces
EMR SOGI | service | patient medical record | review | yes | allows capture of pronouns, non-binary genders, diverse sexualities and better care
Breastfeeding procedure | policy | Organisational procedure relating to provison of space and breaks for feeding/expressing | review | yes | amended wording to be inclusive of gender diverse parents. Considered provsion of space in facilities beyond main buildings
Participant Information and Consent (PICF) forms | program | Form that explains to research participants the necessary information regarding their trial | review | yes | "language updated to be more appropraite for and inclusive of trans participants, as well as non-binray sexes and genders. Suggested removal of term ""master"": and replacing with more modern terms." | Yes | changed langauge that was insensitive to colonial history
PICF guidance document | program | guidance for researchers to inform the development of their PICF | review | yes | consideration of diverse sexes and genders included. | Yes | included consideration of needs of people with disability and a more nuanced description of langauge barriers
IMPORTANT: When inserting new row(s) to this table, please ensure they are inserted above these two black rows.
Example(s)
Title | Subject | Description | Status | Confirm if actions taken | Describe actions taken | Confirm intersectionality considered | Explain intersectional lens applied
Example: Sports ground use and permits policy | Policy | This policy guides the hire and use of all Council's sportsgrounds and facilities by sports clubs and the public. The policy outlines eligibility criteria for hire and use, selection and booking process, fees, payment options, cancellation options and expectations of use. | For review | Yes | Amended the policy to include a commitment to allocate 30% of the total sportsground hiring capacity to new and recently established sports teams comprising of women and gender diverse people. Amended the policy to include a commitment to support local clubs to conduct respect and responsibility training to promote gender equality. Amended the policy to include a commitment to provide dedicated womens and all-gender secured changerooms and facilities for all womens and gender-diverse teams who hire Council sportsgrounds. | Yes | Council conducted research and participated in consultation to ensure the GIA considered intersectionality. It was identified that language and shared changeroom facilities are percieved as major access barriers for culturally and linguistically diverse (CALD) women. Council has addressed these concerns in amending the policy, committing to implementing private changeroom areas and increased signage in a variety of languages.

## 2.1 Strategies and measures
Strategies and measures
Table 2.1 - Strategies and measures progress
Required | Required | Required | Recommended | Recommended | Recommended | Recommended
Strategies and measures | Status | Status description | Evaluation of success | Timeline | Responsible | Relevant indicator(s)
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | Indicators key
List your organisation’s strategies and measures. Include one strategy or measure per row. These are the planned actions that you have outlined in your GEAP to promote gender equality in your workplace. | Assign each strategy or measure a status from the following list: • ‘Complete’ indicates that all planned activities related to this strategy or measure have been finalised. • ‘In progress’ indicates that the activities under this strategy or measure are progressing but not yet complete. • ‘Ongoing’ indicates that the activities under this strategy or measure do not have an end-date and will be addressed on a continual basis. • ‘Not started’ indicates that the planned activities related to this strategy or measure have not yet commenced, including those that are intended to commence in future years. This should include strategies or measures that have been delayed. • ‘Void’ indicates that this strategy or measure appeared in your defined entity’s GEAP, but has since been cancelled. | Describe your progress in implementing each strategy or measure in your GEAP. In particular, you need to explain: • Why you have selected that status from the drop-down menu; and • Whether the status indicates any delay or change from what was planned in your GEAP and if so, the reason for this change. | Evaluating the success of each of your strategies or measures may include: • tracking against pre-identified success markers. These markers may have been specified in your GEAP. • other evaluation markers that may not have been specified in your GEAP, such as participation levels, outcomes, or changes resulting from the strategy or measure, • other ways the strategy or measure has contributed to promoting gender equality in your defined entity. | If your GEAP included a timeline for action or implementation for your strategies and measures, include this timeline below. If you did not include a timeline in your GEAP, we highly recommend you do so in this progress report by including a timeline below. | Include the role or team responsible for implementing of each strategy or measure. | Identify one or more indicators for each strategy or measure that the action was designed to address. See the Indicators key to the right of this table for a description of each workplace gender equality indicator. | [6 empty] | 1. 2. 3. 4. 5. 6. 7. | Gender composition of all levels of the workforce. Gender composition of governing bodies. Equal remuneration for work of equal or comparable value across all levels of the workforce, irrespective of gender. Sexual harassment in the workplace Recruitment and promotion practices in the workplace. Availability and utilisation of terms, conditions and pratices relating to: - family violence leave - flexible working arrangements - working arrangements supporting employees with family or caring responsibilities Gendered segregation within the workplace
Strategies and measures | Status | Status description | Evaluation of success | Timeline | Responsible | 1 | 2 | 3 | 4 | 5 | 6 | 7
Undertake a communication campaign to engage staff and leaders in understanding the case for change and raise awareness of the steps they can take to promote equity in the workplace. | Complete | During the development of the Action Plan messages have been shared via email, Workplace posts, meetings and forums. More are planned to promote it's implementation. Several targetted messages have been shared in Workplace groups such as the LGBTIQA+ Staff and Allies group, within the Safety Champions These messages will continue to be woven into ongoing events and campaigns | Eg of reach: WiP 2022 18 WP posts with 23929 views 17 shares and 628 likes IDPwD - '21 seen by 2.3k 4 comments 1 share 38u reactions. '22 6 posts seen by 4.7k 11 comments 10 shares 65 reactions. Approx 100 visitors to stall. PMS qn: Snr leader inclusion - new qn result slight increase (72/73) PMS qn: Manager inclusion - new qn dig result unchanged (86/86) new qn value 83/84 | 2022 | People and Culture (Communications and Media, Public Affairs) | X | X | X | X | X | X | X
Promote and deliver a range of events that celebrate our diverse workforce and community. | Ongoing | IWD week of events Wear it Purple Week 16 Days fo Activism IDAHOBIT celebrations including drag performer visit and flag raising Workplace and Facebook posts to promote. International Day of Disability Refugee Week Deaf Awreness Week | IWD 2023 5 events - 1530 unique view PMS qn: Snr leader inclusion - new qn result slight increase (72/73) PMS qn: Manager inclusion - new qn dig result unchanged (86/86) new qn value 83/84 | 2022-2026 | Safety Culture Allied Health Staff Voice Committees (Communications and Media, Public Affairs) | X | X | X | X | X | X | X
Embed inclusive principles and practice into development of next strategic plan. | Not started | no work undertaken to date - next strat plan due 2025 | PMS qn: Snr leader inclusion - new qn result slight increase (72/73) | 2024-2025 | TBC | X | X | X | X | X | X | X
Set and monitor diversity targets for The Melbourne Way Leadership Program. | In progress | Diversity data collected for applicants in 2022 and 2023. Gender balance good for men and women, lack of gender diverse people and other diverse identities Messaging updated to encourage applications from more diverse staff |  | 2022 | Leadership Culture and Learning | X | [5 empty] | X
Embed expectation that it is the leaders’ role to create a welcoming and inclusive workplace (linked to safety to speak up). | In progress | Project with safety champions on the impact of incivility on staff and patients, and empowering bystander action. Change management training includes focus on experiences of people - empathy. New manager welcome touches on DEI - will be enhanced. Leadership Masterclasses have included focus on psychological safety. Respect video developed and promoted widely. | PMS Qn: Manager inclusion - new qn dig result unchanged (86/86) new qn value 83/84 PMS Qn: Take setssp to eliminate up 4 to 73 PMS Qn: Encouarges respectful up 85 to 87 PMS Qn: snr psych safety up 62 to 64 PMS Qn: comms psych up54 to 58 PMS Qn: tolerate conduct up 70 to 77 | 2022-2026 | Leadership Culture and Learning | X | X | X | X | X | X | X
Review Leadership Development offerings to enhance inclusive leadership skills including: · managing micro-aggressions · Aboriginal cultural awareness · Disability Awareness · LGBTIQA+ inclusion | In progress | Bystander training developed, piloted, and delivered. Training facilitators form across RMH to assist roll out. Bias 101 session developed and delivered to mulitple teams Disability awareness under review Trans and gender diverse training developed and ready via eLearning Asking the Question training reviewed and launched DCA membership obtained and offerings regularly promoted. |  | 2022-2023 | Safety Culture Allied Health Nursing Education Medical Education Quality, Improvement and Patient Experience | X | [5 empty] | X
Examine impact of leave and flexibility on career progression and develop recommendations. | Not started | no work undertaken to date | PMS Qn: flex work grouping increased 61/73 | 2024 | People & Culture Allied Health Nursing Workforce Medical Workforce | X | [5 empty] | X
Curate an online resource library on a range of diversity, equity and inclusion topics. | In progress | Initial list developed and circulated for feedback and additions. Working with comms to determine best place to house the library within current technical constraints | PMS Qn: Manager inclusion - new qn dig result unchanged (86/86) new qn value 83/84 PMS Qn: Workgroup inclusion - new qn only in 22 not 21 slight increase - 81/84 | 2023 | Leadership Culture and Learning | X | X | X | X | X | X | X
Embed process to ensure systematic policy review considers diversity and inclusion. | In progress | Meetings held with clinical and non-clinical policy review committees. Policy, Procedure and Guideline Development and Review Protocol and Template Procedure was updated as follows: - Purpose and scope includes equity consideration - Definitions gives an overview of what equity means - Responsibilities of author - Development and review include a requirement to consider equity and - template will have a prompt on considering equity. - Submission checklist also require equity consideration. | PMS Qn: Org Integrity grouped slight decrease 77/75 ** add breakdown | 2022 | Quality, Improvement and Patient Experience | X | X | X | X | X | X | X
Identify and review key workforce procedures related to employee experience e.g. reasonable adjustments. | Ongoing | Key policies reviewed include Family Violence, Leave, Child Safety and Breast/chest feeding | PMS Qn: Org Integrity grouped slight decrease 77/75 ** add breakdown | 2022-2026 | People, Culture & Safety | X | X | X | X | X | X | X
Review Board induction processes with the aim of embedding inclusive practice and principles. | Not started | no work undertaken to date | PMS Qn: Snr leader inclusion - new qn result slight increase (72/73) | 2023 | Executive Director People, Culture and Safety, General Counsel |  | x
Review staff orientation processes to embed inclusion. | In progress | Revision of online component complete. As part of recruitment review met with key stakeholders from craft groups across RMH to build understanding of current practices and challenges, completed a literature review and have developed draft reccomendations. | PMS Qn: Snr leader inclusion - new qn result slight increase (72/73) Manager inclusion - new qn dig result unchanged (86/86) new qn value 83/84 | 2022-2023 | People, Culture & Safety Nursing Workforce/Education Medical workforce | X | X | X | X | X | X | X
Support existing staff voice committees and their associated Action Plans – for example: Aboriginal Governance Committee and LGBTIQA+ Steering Committee. | Ongoing | Committees continuing well, increased lived expereince representation on First Nations committee. Disability Action Plan under review, as is the Aboriginal Employment Plan. |  | 2022-2026 | Allied Health People, Culture & Safety | X | [5 empty] | X
Implement a staff voice committee that allows staff living with or caring for someone with disability to shape strategic actions. | Complete | Staff with lived experience targetted to join existing Disability Committee. Will need to monitor and ensure represnattion remains high |  | 2022 | Allied Health Quality, Improvement and Patient Experience People, Culture & Safety | X |  |  |  |  | x | X
Grow pathways programs to increase representation of diverse communities in RMH workforce. Initial focus groups: Disability, TGD and Aboriginal and Torres Strait Islander. | In progress | Working group have developed a centralised model for First Nations Pathways programs. Seeking funding. IPP program for students with disability is ongoing. |  | 2024 | People & Culture Allied Health Workforce Nursing Education and Training Medical Education | X |  |  |  |  | X | X
Review recruitment procedures and templates for inclusive language and practice. | In progress | Key stakeholders engaged. Met with representatives from craft groups across RMH to build understanding of current practices and challenges, completed a literature review and have developed draft reccomendations. | PMS Qn: Equal promo 22-57/23-58 Fair recruit 22-53/23-56 Satisfied L&D 21-62/23 -68 Satisfied opps progress 22-58/23-62 | 2022-2024 | Recruitment Team (Allied Health) (Workforce) (Nursing Workforce) (Medical Workforce ) |  |  |  |  | X
Develop inclusive communications guide. | In progress | Language guide drafted and shared widely for feedback from diverse groups. Nearly complete. | PMS Qn inclusive comms: All staff slght increase 85-88 First Nations sig icrease 76-88 GD sig increase 66-73 LGB sig increase 77-88 Dis increase 74-82 | 2022-2023 | Strategic Communications and Media, Public Affairs | X |  |  |  | X |  | X
Strengthen diverse representation of RMH in external communications | In progress | Comms intent on reflecting diversity in both internal and external messaging. A quarterly audit will capture data from social media. First audit can has been completed. | PMS Qn inclusive comms: All staff slght increase 85-88 First Nations sig icrease 76-88 GD sig increase 66-73 LGB sig increase 77-88 Dis increase 74-83 | 2022-2023 | Strategic Communications and Media, Public Affairs | X |  |  |  | X |  | X
Improve website accessibility and content regarding support for diverse patients/consumers | Complete | New Website launched with AAA accessibility and simple English were possible. | PMS Qn inclusive comms: All staff slght increase 85-88 First Nations sig icrease 76-88 GD sig increase 66-73 LGB sig increase 77-88 Dis increase 74-84 | 2022-2023 | Strategic Communications and Media, Public Affairs | X |  |  |  | X |  | X
Review flexible work procedure and develop communication campaign to raise awareness of the various types and benefits of flexible work to staff and leaders. | In progress | Flex Work procedure reviewed and promoted. Roadshow planned to promote alongside Family Violence Parental leave etc. | PMS Qn: flex work grouped increased 61/73 | 2022-2023 | Strategic Communications and Media, Public Affairs People, Culture & Safety | X |  |  |  |  | X | X
Implement a communication campaign promoting parental leave for people of all genders. | In progress | Roadshow planned to promote alongside Family Violence Flex Work etc. |  | 2022 | Strategic Communications and Media, Public Affairs People, Culture & Safety | X |  |  |  |  | X | X
Implement a communication campaign to promote Family Violence Leave and other supports for people of all backgrounds and identities. | In progress | Procedure under review. Entitlements promoted to staff through internal comms channels. | numbers of people taking significantly increased for all genders (total up from 12 to 60). PMS Qn: support for FV leave up 75 to 81% | 2023-2024 | Strategic Communications and Media, Public Affairs People, Culture & Safety | [5 empty] | X
Develop Workforce Ombuds role/service and monitor insights. | Ongoing | • Position Appointed at 1EFT • Position busy raising awareness of the role across the hospital and supporting staff and management. 288 cases bought and 754 visits in the first 18 months of operations. Most staff visit over 2—3 sessions. • The most frequent issue raised are disputes or conflicts in staff/manager relationships, in relation to respect/treatment, communication or perceived bullying. • Visitors have reported they most value having a safe, confidential setting to explore their concerns, and evaluate options for resolution. They perceive the office to be confidential, impartial, independent and informal. • Quarterly reports have been presented to CEO outlining key themes identified by staff visiting the Workforce Ombuds. Action taken in response has included a revision of the Resolution of Workplace Complaints process, and introduction of restorative practices for systemic or group disputes. | PMS Qn: cultural safe -increase 87 Workgroup inclusion increased 81-84 | 2022 | People, Culture & Safety | X |  |  | X |  |  | X
Appoint OVA Specialist Nurse Advisor (Sexual safety & discrimination) to undertake a review of sexual harassment in the workplace. | Ongoing | Position Appointed at .6EFT Position busy. PMS data shows marked increase in satisfaction with handling of complaints (53%-->73%). Developing a framework for responding to sexual harassment - this will be done in partnership with key stakeholders from across RMH. Linked to OVA strategy. | total formal reports are down 155 - but more through to HR Sex harras satisfaction up signif - 53-72 31% told manager PMS Qn: org integ group up 72-75 steps to eliminate 70-73 encourages respect 85-87 doesn’t tolerate improper 70-77 | 2022-2025 | People, Culture & Safety |  |  |  | X
Partner with diverse staff to review current complaints handling process to ensure a trauma informed and equitable approach. | In progress | RMH actively reviewing this. IHI have reviewed procedures and sought RMH actively reviewing this. IHI have reviewed procedures and sought feedback from some employers. Exploring restorative practice - several P&C staff now attended training. Principles of psychological safety, no blame, group work. Half day workshop will be held to see how these princples can be overlayed with procedures. Trialling process with two teams. Also connected with Griffiths Uni looking at 'Just Culture' model from UK. Preliminary meeting held with Chief Medical Officer and some doctors. Hope to look at clinical procedure in medical space and complaints process. | PMS Qn: bullying satisfaction - down slightly 30-27 discrim satisfaction down signif 63-7 Sex harras satisfaction up signif - 53-72 org integ group up 72-75 steps to eliminate 70-73 encourages respect 85-87 doesn’t tolerate improper 70-78 | 2022-2024 | People, Culture & Safety | X |  |  | X
Further interrogate audit data regarding pay equity to gain a nuanced understanding and develop effective actions in response. Initial focus: · Directors · Senior Medical staff " | In progress | Decision made to revise levels for pay equity audit to allow for imprved data in 2023. This data then can be better intrerrogated and acted upon. Medical Services Directory reviewed HoU allowance and applied more consistent pay. Challenge in medicine is that much is outside of the control of RMH | pay gap reduced from 32-26for women and 57 to 23 for non-binary | 2022-2026 | Finance Systems-SAP Payroll Medical Workforce |  |  | X
Further investigate key gender-segregated workgroups (e.g. medical specialities, security, and hotel services) and develop recommended actions | In progress | Decision made to revise levels for audit to allow for improved data in 2023. This data then can be better intrerrogated and acted upon. Security actively looking to increase number of women. Challenge in medicine is that much is outside of the control of RMH | signifcant increase in non-binary staff across org. more recruits than exits for women in medicine | 2022-2026 | Medical Workforce Security People, Culture & Safety | X
Establish cross organisation Working Group to define data and reporting needs for current and future systems. | In progress | Working group formed. Mapping of data completed. HRIS project scoping phase underway | New HRIS system coming in 2024 | 2022-2026 | Finance Systems-SAP Payroll Medical Workforce | X | X | X | X | X | X | X
Select one
IMPORTANT: When inserting new row(s) to this table, please ensure they are inserted above these two black rows.
Example(s)
Strategies and measures | Status | Status description | Evaluation of success | Timeline | Responsible | Relevant indicator(s)
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7
Example: Address gaps identified in collecting intersectional data as part of employee and payroll systems | Complete | This strategy was implemented in March 2023. A payroll systems firm was engaged to upgrade our systems to support the collection of intersectional data in relation to sexual orientation, race, Aboriginality, religion, ethnicity, disability and gender identity. We have now begun collecting intersectional data and addressing the gaps identified in our 2021 audit. | Although originally anticipated for implementation in 2022, delays meant this strategy was implemented in March 2023. Intersectional data is being collected as part of new recruitments and promotions, and voluntary updates by existing staff. New intersectional data as part of our 2023 progress audit and future GEAPs will enable us to better understand intersectional gender equality in our organisation and areas for improvement. | 2022 | People and Culture Corporate Support | X | X | X |  | X | X | X

## 2.2 Resourcing your GEAP
Resourcing your GEAP
Table 2.2 - Allocation of resources to implement the strategies and measures in your GEAP
Recommended
You might consider some or all of the following, in addition to any other aspects you consider relevant: • Who implements the strategies and measures in your GEAP? What role do they perform at what level in your defined entity? • How many staff members/FTE are allocated to implementing the strategies and measures? • Was enough resourcing allocated to successfully implement your strategies and measures? If not, how will this be addressed?
Your Comments
RMH has committed to a senior role at .8EFT to oversee and drive this work across RMH - the DEI Consultant who reports directly to the Chief People Officer. The DEI Consultant meets regularly with all Executive members to support the implementation and resourcing of the Action Plan. A quarterly report on the Action Plan is provided to a committee comprising executive and other senior leaders. Each action has lead teams and executive sponsorship. Some are further supported by staff voice committees. Each staff voice committee has an executive sponsor, is chaired by a senior leader, and has representatives from across the organisation. A procedure is in development to ensure participation on these committees is recognised and remunerated appropriately. Our Gender Equity and LGBTIQA+ Committees now have an annual budget of $10k to deliver initiatives. The DEI Consultant also works closely with patient facing roles such as our Disability and LGBTIQA+ Liaison Services, and our First Nations Health Unit Completing the audit is possibly the most resource intensive task required under the Act. It requires staff from multiple teams to collect data and ensure it is in a suitable format for submission - not an easy task given the way most payroll systems work. Then it takes signifcant amounts of time to extract the relevant data for analysis and presentation it in a suitable format. Neither the Gender Equality Commission nor Public Sector Commission portals allow for analyis of multiple data points at once, or for easy manipulation of data. Therefore these must be extracted into a s/s for review and analysis. It would be helpful and time-saving if the portals were more sophisticated.

## 3 Indicators
Workplace Gender Equality Indicators
Table 3 - Workplace gender equality indicators progress
Required | Required | Required | Recommended | [6 empty] | Recommended | Factors key:
|  |  | Factors | [7 empty] | a. b. c. d. e. f. g. | The size of the defined entity, including the defined entity's number of employees. The nature and circumstances of the defined entity, including any barriers to making progress. Requirements that apply to the defined entity under any other Act, including an Act of the Commonwealth. The defined entity's resources. The defined entity's operational priorities and competing operational obligations. The practicability and cost to the defined entity of making progress. Genuine attempts made by the defined entity to make progress.
Indicator | Confirm if progress made | Progress description | a | b | c | d | e | f | g | Factors discussion
This column contains the seven workplace gender equality indicators. Complete the 'required' fields, and you are encouraged to complete the 'recommended' columns, to the right of each indicator. | Indicate whether your organisation has made progress in relation to the workplace gender equality indicators. Use the drop-down menu in the cell to select 'yes' or 'no.' | Demonstrate your progress in relation to each workplace gender equality indicator. In this column, please explain why you believe changes in your data do or do not represent progress against each indicator. Refer explicitly to quantitative changes in the data between your previous workplace gender audit and your progress audit. If you wish, you may also make reference to any strategy or measure from your GEAP that supported, or was designed to support, progress against that indicator. | Indicate below whether or not one of these factors has affected your organisation's progress against each indicator. You are encouraged to reference these factors in your discussion in column L. See the Factors key to the right of this table for a description of each factor. | [6 empty] | If you have selected 'yes' to any of the factors in the recommended columns to the left, you are encouraged to complete this column. This column allows you to discuss each factor that has affected your organisation's progress in relation to any of the workplace gender equality indicators.
Indicator | Confirm if progress made | Progress description | a | b | c | d | e | f | g | Factors discussion
Gender composition of all levels of the workforce | Yes | RMH remains a feminised workforce. The number of non-binary people in our organisation has increased 2 fold (92 to 165) and they now are now represented in permanent ongoing positions, and are in more senior roles when compared with 2021. RMH has worked hard to build awareness and inclusion for non-binary and gender diverse people including internal campaigns and events, training, and advocacy. Women are still more likely to work part-time than men (52% and 38%) but the number has risen has for men. Women are more likely to have ongoing positions when compared to men (65% and 45%). Medical staff are one of a few areas that have more women than men, and this year there were more women recruited than exited into these roles. | Yes | Yes | Yes | Yes | Yes | No | Yes | Health is a heavily feminised industry, with pipeline issues for all defined entities. There is also a great deal of training and recruitment practices controlled by bodies extrenal to our organisation such as medical boards.
Gender composition of governing bodies | No | Our board is appointed by the State Government. We remain well balanced with men and women, but with no non-binary board members, and not overly diverse in other ways. We are committed to improve our board induction to enhance DEI thinking and awareness at the board level. | No | Yes | No | No | No | No | No | State government controls board appointments.
Equal remuneration for work of equal or comparable value across all levels of the workforce, irrespective of gender | Yes | Our overall pay gap has decreased for both women and non-binary staff members in nearly every measure since 2021. For example mean base salary was 31.7 and 56.2 in 2021 and is now 26.1 and 22.8. This is due in part to a more nuanced approach the pay equity calculations in compared with last year, and the greater number of non-binary staff members will mean more stable average figures. Efforts have been made to address pay gaps in senior medical staff, who were highlighted last audit and this audit they did not stand out. | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Health is a very competitive industry, facing severe staff shortages. This makes it easier for some staff to negotiate wages. Further, with many medical staff working multiple positions across different hospitals, public and private, there is extra pressure to match wages.
Sexual harassment in the workplace | Yes | Increased recognition and awareness of sexual harasment has resulted in higher rates reported in the PMS. This initial uptick is a good thing. The proportion of people who told the person it was not ok has increased from 43 to 49%. 31% told a manger, up from 25% in 2021. Many more of those who did report it were satisfied with the outcome this year (72%) than in 2021 (53%). RMH committed to a 3 day p/w psoition to focus on sexual harassment instigated by patients against staff and this has has significant impact. We need to continue to build on and expand this work. Data collection is challenging given the riskman tool which is not owned by RMH - this is used by most public hospitals. | Yes | Yes | Yes | Yes | Yes | No | Yes | The Sexual Safety Nurse Consultant role has been instrumental in driving change. However in an organisation our size and complexity, large scale change is very hard and slow going. There are not always clear lines of reporting/management, some staff have no time outside their clinincal hours to engage with organisational culture initiatives, for med interns their line manager has power over whether they get into their next stage of their career or not, there is a history of putting the patients needs first, and we care for patients with complex needs including delirium. This all exists in a context where we do need to make sure patients are treated before anything else. If a ward is busy, things get dropped, because they have to.
Recruitment and promotion practices in the workplace | Yes | Overall, 71% of new recruits and 68% of exits were women. There were no glaring areas with unexpected levels of exits by gender. Senior Medical Staff had more women recruited than exited, which is pleasing given the known issue in retaining women in medicine compared to men. Currently RMH is unable to report on higher duties, secondments, or promotions, though this is being considered in the new HRIS build. PMS questions related to the recruitment and promotion include professional development, opportunities to progress and the fairness of our recruitment processes. While there has been an improvement since 2022, positive responses in this domain are low when compared to many other PMS areas. We are part way through a review and revamp of our recruitment practices, with changes already made to our website and some templates. We are partnering with some external experts to support aspects of this project. | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Health is a heavily feminised industry, with pipeline issues for all defined entities. There is also a great deal of training and recruitment practices controlled by bodies extrenal to our organisation such as medical boards. This significantly infleunces people's career progression - eg some medical boards do not allow people to train part-time. Many of the large intakes - such as grad nurses and junior medical staff is ccentrally controlled via a matching system. Health is a very competitive industry, facing severe staff shortages. This makes it challenging to encourage managers, who do have control, to slow the recruitment porocess down and make changes that will help to reduce bias through the recruitment process. IT is also harder ot have oversight of all the recruitment processes in such as large and complex organisation. It is expected that new systems in 2024 will allow RMH to monitor secondments higher duties and promotions.
Availability and utilisation of terms, conditions and practices relating to: - family violence leave; and - flexible working arrangements; and - working arrangements supporting employees with family or caring responsibilities | Yes | 60 staff utilised Family Violence leave in 2022/3, comprising 55 women, 3 men and 2 non-binary people. This is a significant increase from 2020/21 when it was 12 women, 1 man and 1 non-binary staff member. Furthermore, most PMS respondents (81% up from 75%) were confident that RMH would support them to access family violence leave if required. However, scores were still lower for nonbinary staff (75%) and those with disability (76% up from 64%). Access to flexible work increased, with only 27%PMS of respondents indicating they did not access flexible work, down from 36% in 2021. Two of the three PMS questions associated with this indicator show positive progress. Agreement that a flexible work application would be considered fairly rose 4%, and expectation that people could access family violence leave rose 6%. The third, that their manager supports flexible working remained steady. These changes are shaped by a review of our flexible work and familiy violence procedures, and internal communications reagrding the review. Work required still for take up of parental leave, and perceptions of carers regarding flex work applications | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Public hospitals are subject to multiple enterprise agreements. These agreements do not always align, or offer the same entitlements. These agreements are negotiated between the unuions and the state government. Funding from the state governement is aligned to these agreements. So there are costs and complexities of going above the agreements.
Gendered segregation within the workplace | Yes | Decrease in reported rates of bullying down to 14% from 19% in 2021. A range of PMS questions related to bullying, harassment and a culture of inclusion were considered. Overall scores have increased in each which is pleasing. Of interest in this section is increase in agreement with the notion that that RMH doesn’t tolerate improper conduct from 70% in 2021 to 77% in 2023, and that RMH has taken steps to eliminate bullying, harassment & discrimination, which has risen from 69% in 2021 to 73% this year. I feel culturally safe at work has risen from 80% in 2021 to 87% in 2023. This is also reflected in some of the strengths identified in PMS free text responses. RMH has engaged in a number of events, activities, communication campaigns, training, and advoacy all aimed at improving cultural safety, reducing problematic behaviour, and better responses to incidents. This has been aligned with our safety culture where people are encouraged to 'speak up' for saafety, respect, inclusion etc. | Yes | Yes | Yes | Yes | Yes | No | Yes | Health is a heavily feminised industry, with pipeline issues for all defined entities. There is also a great deal of training and recruitment practices controlled by bodies extrenal to our organisation such as medical boards. The state government controls the placement/appointment of the bulk of our workforce thorugh our graduate nursing and medical staff. However, we appear to be less feminsied that some of our comparators, and have done much work on the culture and have begun projects in the areas we have more control over such as our security team.

## Examples (hidden)
1 Gender impact assessments
| Title | Subject | Description | Status |  |  | Confirm if actions taken |  |  |  | Describe actions taken |  | Confirm intersectionality considered |  | Explain intersectional lens applied
| What is the title of the policy, program or service that was the subject of the GIA? Please use one row for each GIA completed. When reporting on multiple actions taken, include this information in the relevant single cell. | Was the subject of the GIA a policy, program or service? For definitions of policies, programs and services, please refer to the guidance materials at Appendix A: Glossary of terms. Use the drop-down menu in the cell to select your answer. | Provide a description of the policy, program or service subject to the GIA. | Was the policy, program or service new, or up for review? Use the drop-down menu in the cell to select your answer. |  |  | Were actions taken to develop or vary the policy, program or service to meet the needs of people of different genders, address gender inequality and promote gender equality as a result of the GIA? Use the drop-down menu in the cell to indicate whether or not actions were taken as a result of the GIA. |  |  |  | Describe the actions taken to develop or vary the policy, program or service to meet the needs of people of different genders, address gender inequality and promote gender equality. When reporting on multiple actions taken, include this information in one cell. You can press alt+enter to include new lines. |  | Was it considered that gender inequality may be compounded by disadvantage or discrimination that people may experience on the basis of intersectionality? Use the drop-down menu in the cell to select your answer. |  | Explain how an intersectional lens was applied while completing the GIA. If this was not done, explain why this was not practicable.
| Example: Sports ground use and permits policy | Policy | This policy guides the hire and use of all Council's sportsgrounds and facilities by sports clubs and the public. The policy outlines eligibility criteria for hire and use, selection and booking process, fees, payment options, cancellation options and expectations of use. | For review |  |  | Yes |  |  |  | Amended the policy to include a commitment to allocate 30% of the total sportsground hiring capacity to new and recently established sports teams comprising of women and gender diverse people. Amended the policy to include a commitment to support local clubs to conduct respect and responsibility training to promote gender equality. Amended the policy to include a commitment to provide dedicated womens and all-gender secured changerooms and facilities for all womens and gender-diverse teams who hire Council sportsgrounds. |  | Yes |  | Council conducted research and participated in consultation to ensure the GIA considered intersectionality. It was identified that language and shared changeroom facilities are percieved as major access barriers for culturally and linguistically diverse (CALD) women. Council has addressed these concerns in amending the policy, committing to implementing private changeroom areas and increased signage in a variety of languages.
2.1 Strategies and measures
| Strategies and measures | Status | Status description | Evaluation of success | [6 empty] | Timeline | Responsible | Relevant indicator(s)
[13 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7
| List your organisation’s strategies and measures. Include one strategy or measure per row. These are the planned actions that you have outlined in your GEAP to promote gender equality in your workplace. | Assign each strategy or measure a status from the following list: • ‘Complete’ indicates that all planned activities related to this strategy or measure have been finalised. • ‘In progress’ indicates that the activities under this strategy or measure are progressing but not yet complete. • ‘Ongoing’ indicates that the activities under this strategy or measure do not have an end-date and will be addressed on a continual basis. • ‘Not started’ indicates that the planned activities related to this strategy or measure have not yet commenced, including those that are intended to commence in future years. This should include strategies or measures that have been delayed. • ‘Void’ indicates that this strategy or measure appeared in your defined entity’s GEAP, but has since been cancelled. | Describe your progress in implementing each strategy or measure in your GEAP. In particular, you need to explain: • Why you have selected that status from the drop-down menu; and • Whether the status indicates any delay or change from what was planned in your GEAP and if so, the reason for this change. | Evaluating the success of each of your strategies or measures may include: • tracking against pre-identified success markers. These markers may have been specified in your GEAP. • other evaluation markers that may not have been specified in your GEAP, such as participation levels, outcomes, or changes resulting from the strategy or measure, • other ways the strategy or measure has contributed to promoting gender equality in your defined entity. | [6 empty] | If your GEAP included a timeline for action or implementation for your strategies and measures, include this timeline below. If you did not include a timeline in your GEAP, we highly recommend you do so in this progress report by including a timeline below. | Include the role or team responsible for implementing of each strategy or measure. | Identify one or more indicators for each strategy or measure that the action was designed to address. See the Indicators key to the right of this table for a description of each workplace gender equality indicator.
| Example: Address gaps identified in collecting intersectional data as part of employee and payroll systems | Complete | This strategy was implemented in March 2023. A payroll systems firm was engaged to upgrade our systems to support the collection of intersectional data in relation to sexual orientation, race, Aboriginality, religion, ethnicity, disability and gender identity. We have now begun collecting intersectional data and addressing the gaps identified in our 2021 audit. | Although originally anticipated for implementation in 2022, delays meant this strategy was implemented in March 2023. Intersectional data is being collected as part of new recruitments and promotions, and voluntary updates by existing staff. New intersectional data as part of our 2023 progress audit and future GEAPs will enable us to better understand intersectional gender equality in our organisation and areas for improvement. | [6 empty] | 2022 | People and Culture Corporate Support | X | X | X |  | X | X | X
3 Workplace Gender Equality Indicators
| Indicator | Confirm if progress made | Progress description | Factors | [6 empty] | Factors discussion
|  |  |  | a | b | c | d | e | f | g
| This column contains the seven workplace gender equality indicators. Complete the 'required' fields, and you are encouraged to complete the 'recommended' columns, to the right of each indicator. | Indicate whether your organisation has made progress in relation to the workplace gender equality indicators. Use the drop-down menu in the cell to select 'yes' or 'no.' | Demonstrate your progress in relation to each workplace gender equality indicator. In this column, please explain why you believe changes in your data do or do not represent progress against each indicator. Refer explicitly to quantitative changes in the data between your previous workplace gender audit and your progress audit. If you wish, you may also make reference to any strategy or measure from your GEAP that supported, or was designed to support, progress against that indicator. | Indicate below whether or not one of these factors has affected your organisation's progress against each indicator. You are encouraged to reference these factors in your discussion in column L. See the Factors key to the right of this table for a description of each factor. | [6 empty] | If you have selected 'yes' to any of the factors in the recommended columns to the left, you are encouraged to complete this column. This column allows you to discuss each factor that has affected your organisation's progress in relation to any of the workplace gender equality indicators.
| Example 1: Recruitment and promotion practices in the workplace | Yes | Recruitment In our 2021 audit, women represented only 35% of new recruits in the year to 30 June 2021. In our 2023 progress audit, this rose 6% to 41%. In 2021, of the women we recruited, 17% were employed on a full-time permanent basis, 14% on a part-time permanent basis and 69% on fixed-term contracts. In 2023, 22% of women recruited were employed on a full-time permanent basis, 20% on a part-time permanent basis and 58% on fixed-term contracts. We were not able to collect non-binary or gender diverse data in 2021. Our employee and payroll systems have since been updated to collect improved gender-diverse data. This has been achieved through the implementation of strategy 5.2 under our 2021 Gender Equality Action Plan (GEAP): ‘Embed inclusive practices into our HR electronic systems. For example, offering a range of gender selection options’. As such, in 2023, our data showed that 2% of new recruits identified as non-binary or gender diverse. Our organisation argues that these figures, in conjunction with successful implementation of relevant GEAP strategies, contribute to progress against Indicator 5. Not only have we been able to notably increase our recruitment of women and gender diverse employees, but we have also been able to offer these new recruits more attractive contract conditions. Stable contracts will also support us to retain employees of all genders and move towards a more gender-balanced workforce in the future. Promotions Our 2021 audit showed that 25% of promotions in the 12 months to 30 June 2021 were awarded to women. These promotions occurred in the lower and middle levels of the organisation only, and not within the executive leadership team. Our 2023 progress audit showed that 30% of all promotions were awarded to women, an increase of 5%. Of these, 10% occurred in the higher levels of the organisation and were ongoing permanent roles. Our organisation historically has a very stable executive leadership team where roles tend to be longer-term contracts or ongoing positions, with few exits. We are pleased to see promotion at the higher level of our organisation into ongoing positions for women. In 2021, we were not able to collect promotion data for non-binary or gender-diverse employees. In 2023, our updated systems allowed us to collect this data. However, there were no promotions awarded to this staff cohort. We believe that a significant aspect of our success in increasing the proportion of promotions awarded to women has been our focus on improving secondment and higher duties opportunities for women and gender-diverse employees. The proportion of secondments awarded to women increased by 5% and the proportion of higher duties by 6% between our 2021 workplace gender audit and our 2023 progress audit. Data on higher duties opportunities for gender diverse and non-binary employees was not collected in 2021, therefore there is no measured change in the data. We consider these improvements, while small, to demonstrate measurable progress against the workplace gender equality indicator ‘recruitment and promotion practices in the workplace’. We also believe the uptick in career development opportunities for women and resulting increase in women’s share of promotions demonstrates that our strategic approach is effective. We hope to see similar improvements for gender diverse employees reflected in our 2025 data. | No | Yes | No | No | No | No | Yes | As a largely male-dominated industry we recognise we have started from a lower baseline for this indicator and there is further to go. Despite this, we have made genuine efforts to attract and recruit a more gender diverse workforce by implementing the strategies identified in our GEAP, in particular: strategy 5.2 ‘Embed inclusive practices into our HR electronic systems. For example, offering a range of gender selection options’. We note that we are two years into the four-year GEAP implementation period, and as such have not fully implemented all GEAP strategies. The majority of our strategies against this indicator remain in early implementation stage. We believe our genuine efforts to implement strategies against this indicator and measurable progress arising from the data, demonstrate progress against indicator 5.
| Example 2: Sexual harassment in the workplace | No | Our 2021 Employee Experience Survey data showed that 7% of women and 4% of men who responded to the survey had experienced sexual harassment in the workplace, and of those 5% of women and 6% of men made a formal complaint. In 2023, our Employee Experience Survey data showed that 9% of women and 6% of men who responded to the survey reported having experienced sexual harassment in the workplace, an increase of 2% from 2021 for both cohorts. Of those, 9% of women and 10% of men indicated that they had made a formal complaint. Our 2023 Employee Experience Survey also indicated that women with disability were overrepresented among those who reported experiencing sexual harassment. We have initiated a review process to consider how we might address this between now and the 2025 reporting cycle. No respondents in our 2021 Employee Experience Survey identified as gender diverse. We also didn’t record any formal sexual harassment complaints in our 2021 workforce reporting data from employees of self-described gender. In our 2023 employee experience survey, 2% of respondents identified as non-binary or gender diverse. Of this cohort, 10% indicated experience of sexual harassment, with 50% of this group indicating that they had made a formal complaint. We note that these figures represent an increase in anonymous self-reporting of sexual harassment. This is concerning, as anonymous reporting tends to be more accurate than formal incident reporting processes. In analysing our 2021 and 2023 audit data, we found that our workforce reporting shows minimal change in terms of outcomes for formal complaints of sexual harassment. In 2021, our audit data showed that no outcome was reached for 70% of matters where the complainant was a woman, and 50% of matters where the complainant was a man. In 2023, our progress audit showed that of the incidents of sexual harassment reported by women, no outcome was reached for 65% of matters. This figure was 40% for men. We did not collect data on gender diverse and non-binary employees in 2021, nor their experience of sexual harassment. Our 2023 progress audit showed that of the incidents of sexual harassment reported by gender diverse and non-binary employees, no outcome was reached for 67% of matters. The enduring high levels of formal complaints with no outcome across our 2021 and 2023 audit data suggests that we have work to do in effectively and efficiently resolving sexual harassment complaints. The lack of outcomes for incidents of this type may contribute to our lack of progress in reducing sexual harassment. As a result of this analysis, we are reviewing our GEAP strategies and measures to consider how we might better respond to, and therefore hopefully reduce, sexual harassment in our organisation. We consider that the anonymous nature of the Employee Experience Survey data provides an accurate representation of sexual harassment. The increased sexual harassment reported via the Employee Experience Survey data indicates ‘no progress’ was made by our organisation against this indicator. | No | No | No | Yes | Yes | No | No | (e) Competing priorities and operational obligations Our organisation is a metro health service. During the recent covid-19 pandemic, Victoria’s public health system experienced unprecedented demand. In particular, rates of access to ICU and ventilation increased dramatically. As such, our organisation prioritised its public-facing service delivery. We directed the majority of our stretched resources externally to enable high-quality public health care. Demand outstripped supply, and already-stretched resources were directed to keeping ICU and general wards staffed. As a result, we were not able to deliver comprehensive in-person bespoke staff training in relation to sexual harassment, so instead delivered a low-cost e-learning module. We also lacked the resources to comprehensively review our internal sexual harassment processes. (d) Resources As described cell D9, our resources were significantly stretched due to an increase in demand for ICU services during the covid-19 pandemic. Competing priorities reduced the resources available for internal-facing programs, such as comprehensive sexual harassment training delivery and process review. For this reason, we focussed on low-cost strategies and measures in our GEAP, including delivering a sexual harassment e-learning module, circulating internal communications campaigns and encouraging staff to undertake the Employee Experience Survey. Our communications campaign focussed on drawing attention to existing sexual harassment policies including how the organisation will respond.

## (Hidden) REF (hidden)
Policy | New | Yes | Select one | Yes
Program | For Review | No | Complete | No action taken
Service |  |  | In progress
Ongoing
Not started
Void/cancelled